## Sheet1
Task List | Week 3 (13.02 - 17.02) | Week 4 (20.02 - 24.02) | Week 5 (27.02 - 03.03) | Week 6 (06.03 - 10.03) | Week 7 (13.03 - 17.03) | Week 8, 9, 10 (20.03 - 7.04) | Week 12 (17.04 - 21.04) | Week 13 (24.04 - 28.04)
Task 1: Creating prototype in Figma, writing down set of the requirements for the project, timeline planning | Delivered on 20.02 - Finished prototype, timeline, set of requirements
Task 2: Developing the UI base of the project in Kotlin |  | Delivered on 27.02 - Completed UI of the project
Task 3: Developing the BFS algorithm |  |  | Delivered on 06.03 - Working version of the BFS algorithm written in Kotlin
Task 4: Developing the DFS algorithm |  |  |  | Delivered on 06.03 - Working version of DFS algorithm written in Kotlin
Task 5: Linking the UI elements with the developed algorithms |  |  |  |  | Delivered on 20.03 - Finished version of the app with working integrated UI and algorithms
Task 6: Developing the rest of elements stated in project outline (e.g., maze generator), working on the final report | [5 empty] | Delivered on 17.04 - All the elements that were feasible to develop and progress on the project
Task 7: Continue the work on the final report and preparing for the final demonstration | [6 empty] | There will be no deliverables on this part of the project, but there will be progress discussion on 24.04 meeting